## Sheet1
Question | Answer
Will being awarded the planning and design phase preclude the ability to perform the construction/ installation work? | Yes, due to the grant funding the project, the firm that completes the design phase can only oversee implementation, not perform it.
Has the effective FIS model been requested and received from the FEMA Engineering Library? Is the model digital (i.e., HEC-RAS program digital files)? | No, it has not been requested.
Habitat plans were previously created for the property by UWM. Will any of those plans or portions of those plans be incorporated into this project? | This project will start with a clean slate. With this habitat restoration work being conducted as an AOC project, the design will need to be based on meeting the specific AOC goals for fish and wildlife populations.
Who will sit on the RFP review panel? | Drew Shuster from Schlitz Audubon, Kelly Hayden from WDNR, and several other technical experts
Has a Phase 1 cultural resources survey been conducted? | Yes. UWM completed the survey and did not recommend any further work.
Has a Section 7 consultation occurred? | No. See Task 5.1 for information regarding the Consultant's role in the Section 7 process.
Is there a QAPP for the primary Schlitz Audubon property? | No
Regarding the presence/absence wildlife assessments, will additional mussel surveys be required or is existing data sufficient? | Some state threatened mussels have been documented in this stretch of the river. The Consultant will be provided available survey information, though the information available is several years old and may not reflect current conditions. The intent behind the presence/absence surveys is not to monitor wildlife populations but to inform design to ensure populations of sensitive species are avoided/protected during implementation. For example, an understanding of where mussel beds are located may influence the placement of shoreline habitat features for fish or the location of crayfish burrow clusters may impact locations for wetland scrapes.
Will a DNR assured wetland delineator be required? | Project team qualifications should be detailed in the proposal response. The Review Panel will review the qualifications for each project team and score proposals based on qualifications, experience, approach, and cost. The Consultant must be able to complete the wetland delineation task as described in the RFP and secure the appropriate permits for the design.
How does Schlitz Audubon Nature Center (SANC) define the Principal-in-Charge’s position in terms of role and responsibilities as included in the Organization Chart section of RFP? | The Principal-in-charge is responsible for the overall completion of the project and ensuring deliverables meet industry standards.
What is meant by “proposers may have up to 12 staff, but not more.” in the Staff Qualifications section of the RFP? Is that referring to the number of resumes included, or number of staff on the organization chart, or something else? | The staff qualification section is meant for proposals to outline the qualifications of the staff on the organization chart, as well as the staff of subcontractors contributing to the project.
There is no cost estimate row for Task 6.3 Presence/Absence Wildlife Assessment on the provided cost estimate spreadsheet. Should we add or will you add and re-issue? Will subsequent tasks be renumbered? Same applies for Task 8.1 (Focal Species Evaluation and Matrix) | Thank you for identifiying that oversight. Task 6.3 and 8.1 have been added to the cost sheet and is avialble for download on the Schlitz Audubon Cleaver RFP webpage. | Cleaver RFP - Schlitz Audubon
Tasks 2.2, 2.3, and 2.5: For each task, are these meetings in person or virtual only? If hybrid, then how many should we assume are in person? | Meetings for tasks 2.2 and 2.3 may be fully virtutal. Meetings for Task 2.5 are typically virtual, however some projects have benefited from in-person discussion for specific aspects of the project. Consultants could assume that up to one of the Outside Technical Review meeting could be held in-person if desired.
The Request for Proposal (RFP) states a $315,000 not-to-exceed budget. Does this include contingency for Task 9 (implementation oversight) or is Task 9 expected to be contracted separately with new funds? | Task 9, implementation oversite, will be contracted separately with new funds.
When is implementation (Task 9) expected to occur? Will construction oversight (Task 9) require full-time resident inspection or periodic site visits? | Implementation, at the earliest, will start 2028, but is funding dependent. Full-time resident inspection for the duration of implementatoin is not anticipated, though there may be specific short-term (few days) activities that may warrant an increased presence.
Will public meeting facilitation (logistics, notifications, recording) be handled by SANC, or should the consultant budget staff/admin support? Or will the consultant just prepare technical content and presenters? What meeting materials (posters, boards, handouts) will the consultant be expected to prepare for public information meetings? | SANC will facilitate the logistics of public meetings. The consultant will be responsible for content and presenters. The consultant is responsible for preparing meeting materials such as presentations, poster(s) to be displayed at the Nature Center, and handouts.
If field conditions (e.g., extent of landfill rubble, invasive vegetation) expand survey/design needs, will budget adjustments/change orders be considered, or should the consultant assume all risks within the $315,000 not-to-exceed budget? | Change orders can be considered, but are subject to approval by all parties and funding.
Does SANC/Wisconsin Department of Natural Resources (WDNR) have templates, outlines, or example Concept Design Reports and Final Design Reports from prior Area of Concern or GLRI-funded projects that you would like the consultant to follow? Or is deliverable formatting at the consultant’s discretion if content requirements are met? | Formatting is at the consultants discretion, as long as the deliverables outlined in the RFP are met.
Does SANC/WDNR have a preferred detailed project schedule for the concept planning and final design phases (e.g., anticipated submittal/review cycles, timeframes for Technical Team review, turnaround expectations for comments)? Or should the consultant plan to propose a detailed schedule aligned with the high-level milestones provided in the RFP? | It is up to the consultant, and should be reflected in their project approach description.
Can you clarify who will review and provide consolidated feedback on the draft Concept Design Report, 60%, 90%, and Final Design deliverables? For example, will drafts be reviewed by only SANC/WDNR project managers, or will the Technical Team, EPA, or the Community Advisory Committee also provide formal feedback at each stage? | The Tech team will review the 30%, 60% and 90% draft stages, as outlined in Task 2.5. CAC members and EPA have representation on the Tech Team and will not be engaged separately for review.
Will consultant responses to comments be expected in a formal comment-response matrix for each draft, or will informal responses/redlines be acceptable? | There is no formal comment-response format. The consultant must demonstrait how each comment was addressed or resolved, however the format for collecting feedback and documenting responses can be determined by consensus of the Project Team (consultant, SANC, DNR)
Should the consultant budget for multiple review cycles at each stage (e.g., internal WDNR review followed by Technical Team review), or will SANC/WDNR consolidate comments before returning them to the consultant? | SANC/WDNR will condut a cursory review of deliverables before they are provided to the Tech Team for comment. The consultant may recieve some feedback from the cursory review regarding "big-picture" topics to be resolved before the deliverable can be shared with the Tech Team. Comments made by SANC/WDNR beyond the cursory review will be returned to the Consultant along with Tech Team comments.
For the species eval matrix, should the consultant consider seasonal habitat needs (e.g., breeding, overwintering, migration stopovers) or only breeding-season support? | The goal of the project is to improve habtitat to support breeding populations. The matrix is designed to show how actions will benefit or hinder that goal. To support populations, secondary considerations for other reasonalbe seasonal habitat needs can be considered.
Should the consultant plan to include a full prescribed fire plan with burn units, smoke management, and permitting details, or just acknowledge prescribed fire as a potential tool in the maintenance plan? | It is up to the consultant if burning will be a implementation technique. If so, it should be reflected in their project approach description.
For Task 9, will SANC/WDNR or the implementation contractor be responsible for obtaining local approvals/permits for prescribed burning (e.g., municipal fire department, county), or should the consultant budget for those efforts? | Permits for burns during the implementation phase will be the responsibility of the implementation contractor. Any permits for burns as part of the maintenance plan, will be the responsibility of SANC. The exact scope of work and responsibilities for implementation oversite will be determined after the design phase is complete and if funding is available.
how many ephemeral ponds there are in total on the property? | Two
Do you expect water level monitoring as part of this project? | It is up to the consultant, and should be reflected in their project approach description.
Is there any flexibility in the project timeline, such as completing the final design sooner than April 2028? Is the stated timeline tied to the grant funding for the project? | The Consultant may present an alternative timeline, however the end date should not extend past the date listed in the RFP.
Survey has been included as a task in the RFP scope. Is the intent to complete a full topographic survey of the entire property or just adjacent the river where potential restoration work would be affecting the banks and riverine conditions of a hydraulic model? A full-site survey may be very costly and take needed funds away from time spent on other field investigations, design and alternatives analyses. | A 1-ft topographic map of the will be provided to the selected consultant as part of the historic data review. It is up to the consultant to determine where additional topographic surveys are needed to inform design, and should be reflected in their project approach.
Does the Schlitz Audubon own to the center of the river/west bank of the river/other location? Does the bathymetric survey need to traverse the entirety of the river or just the areas of proposed improvements? | It is up to the consultant, and should be reflected in their project approach description. It should be assumed that Schlitz Audubon owns to the center of the river along their shoreline, including the islands that are scattered throughout the main channel.
How extensive is the WDNR side scan information and bathymetry data that was noted in Task 4 of the RFP? What year was the data collected? | The bathymetry data includes the main channel from County Line Road downstream to N Range Line Road and was collected prior to 2023
Is there a map of the location/limits of the historic landfill? | The known extent of the landfill can be found from the USGS soil maps
Can you provide the complete list of AOC wildlife focal species for the site and those that have been identified at the site. Also, can you provide the list of "do no harm" species. | A full list of focal species and "do no harm" species for the Cleaver property will be provided to the selected consultant. Additional information regarding focal species can be found in the Mangement Action List for the Degredation of Fish and Wildlife Populations which is available on the DNR webpage for the Milwaukee Esutary AOC | Milwaukee Estuary Area of Concern ¦ ¦ Wisconsin DNR
Can you provide a copy of the 2018 wetland delineation that is mentioned in Task 4 of the RFP. | Attachment D is the map provided during the property site vists, which includes the 2018 wetland delineation.